## Slide 1: XL-C Project Review SW Content
July 14th, 2013
Copyright © 2013 Stratasys Ltd. All rights reserved.
Company Confidential

## Slide 2: XL-C SW - Executive Summary
Copyright © 2013 Stratasys Ltd. All rights reserved.
Software Summary |  |  | 
Task | Block - Flooding | Block – Non Flooding | Comments
XL-B Infra |  |  | 
XL-B Known Content |  |  | 
XL-C Milestone #2 |  |  | 
XL-C Milestone #3 |  |  | 
XL-C Milestone #4 No SHS |  |  | 
XL-C Milestone #4 With SHS |  |  | 

## Slide 3: XL-B
Copyright © 2013 Stratasys Ltd. All rights reserved.
SW Infra |  |  | 
Task | Duration | SW Content | Pre-requisites
Unified FOM baseline | 2 MM (started) – OR – 6 MM | ‘Eden Mode’ = no DM, no mixed parts, but can be mixed tray (Unified baseline for OCB only) – OR – ‘Eden Mode’ = no DM, no mixed parts, no mixed tray + GUI (“disguise” to Eden machine today) | None
Optimize SW Infra | 1 MM 1 MM 1 MM | Static analysis for entire FOM projects Memory management fixes Separate wizards logics from GUI | None

## Slide 4: XL-B
Copyright © 2013 Stratasys Ltd. All rights reserved.
SW Infra |  |  | 
Task | Duration | SW Content | Pre-requisites
Scattering dll | 1 MM (started) | Share scattering logic and code for Printing (EM side) and Estimations (OS side) | None
Continuous model size | 3 MM | Avoid S/M/L models for simplicity | None
New IDE – XE3 | 3 MM (started) | Migration of Trunk projects (Objet FOM machines) | None
XL – A bug fixes | TBD |  | 

## Slide 5: XL-B
Copyright © 2013 Stratasys Ltd. All rights reserved.
System requirements with SW content |  |  | 
Task | Duration | SW Content | Pre-requisites
Internal Heating | Will be estimated after SRS review Rough = 5 MM | SRS not ready (risk to effort estimation) Working with external controllers Implement communication protocol using RS485 (new serial communication protocol in system) Implement system response to controller alerts | Spec Machine availability for tests
External waste | 1 MM | Adaptation for working with 3 MSC boards | Spec Machine availability for tests
Internal UV sensor | 1 MM | Import existing generic UV wizard from Objet500 + adaptations to Objet1000 | Spec Machine availability for tests

## Slide 6: XL-B
Copyright © 2013 Stratasys Ltd. All rights reserved.
Potential additional SW effort |  |  | 
Task | Duration | SW Content | Pre-requisites
New motor on Z | ? | SW effort needed? | SRS ready and reviewed Machine availability for tests
Roller pump | ? | SW effort needed? (does this refer to RSS ? If yes, SW is implemented) | SRS ready and reviewed Machine availability for tests
Power Unit | ? | SW effort needed? | SRS ready and reviewed Machine availability for tests
Stepper pumps | ? | SW effort needed? | SRS ready and reviewed Machine availability for tests

## Slide 7: XL-C Milestone 2 (Jetting Station)
Copyright © 2013 Stratasys Ltd. All rights reserved.
Software - Milestone 2 |  |  |  | 
Task | Duration C1 | Duration C2 | SW Content | Pre-requisites
Tester adaptation | 2 MM | same | Additional Special FPGA code may be required. | Spec. OHDB2 and Data card final hardware schematics.
OHDB2 MCU Software | 1 MM | same | Not including ethernet. | Spec. OHDB2 and Data card final hardware schematics.
HW-SW integration | 1 MM | same |  | Final hardware.
OHDB2 Simulator | 1 MM | same |  | Final hardware schematics.

## Slide 8: XL-C Milestone 3 (Gen4 on Triplex)
Copyright © 2013 Stratasys Ltd. All rights reserved.
Software - Milestone 3 |  |  |  | 
Task | Duration C1 | Duration C2 | SW Content | Pre-requisites
New Nozzles mapping | 1 MM | same |  | Print Head/Block spec
New printing sequencers | 2 MM | same |  | PQ spec
New Purge / Wiping Sequence | 1 MM | Same |  | Spec
Weights voltages calibration | 2 MM | same |  | Spec
Configurable PH | 3 MM | Same | Using same exe/code for E1 & G4 | Discuss if has benefit and how to do it. Depends also on Flooding/non Flooding.
Integration on the machine |  |  |  | Machine

## Slide 9: XL-C Milestone 4 (No SHS Printing Mode)
Copyright © 2013 Stratasys Ltd. All rights reserved.
Software - Milestone 4 |  |  |  | 
Task | Block - Flooding | Block - Non Flooding | SW Content | Pre-requisites
Heads Filling Calibration Wizard | 1 MM | 2 MM |  | Spec
Wiper Calibration Wizard | 1 MM | same |  | Spec
Head Alignment Wizard | 1 MM | same |  | Spec
Ethernet PC – OHDB data path communication | 6 MM | same |  | Spec
Vacuum Calibration Wizard | 1 MM | 2 MM | Common to block / Per chamber | Spec
MRW | 3 MM | same |  | Spec

## Slide 10: XL-C Milestone 4 (SHS Printing Mode)
Copyright © 2013 Stratasys Ltd. All rights reserved.
Software - Milestone 4 |  |  |  | 
Task | Block - Flooding | Block - Non Flooding | SW Content | Pre-requisites
SHS operation mode | 6 MM | same | Modes manager, Material per mode, System operation … | Spec
SHS 600 DPI Y Sequencer | 1 MM | same |  | Spec
MRW | 3 MM | 36 MM | From Connex/Triplex experience | Spec
HSW / HOW | 6 MM | 15 MM | Due to relation to MRW | Spec
UV calibration wizard | 4 MM | same |  | Spec
SHS Advanced Licensing | 2 MM | same |  | Spec
Objet Studio | 3 MM | same | New mode, Estimations, Flexible parameters. Not including 64-bit. | Spec

## Slide 11: XL-C SW - Executive Summary
Copyright © 2013 Stratasys Ltd. All rights reserved.
Software Summary |  |  | 
Task | Block - Flooding | Block – Non Flooding | Comments
XL-B Infra | 12-16 MM | same | 4 MM depending on ObjetXXX definition. 3 MM done.
XL-B Known Content | 7 MM | same | Must clarify uncertain content
XL-C Milestone #2 | 5 MM | same | Adapting E1 Tester
XL-C Milestone #3 | 9 MM | same | Must be on Triplex
XL-C Milestone #4 No SHS | 13 MM | 15 MM | Can be implemented and tested as part of Milestone #3
XL-C Milestone #4 With SHS | 24 MM | 67 MM | Strongly suggesting Flooding Block!

## Slide 12: Thank You
Copyright © 2013 Stratasys Ltd. All rights reserved.