## Slide 1: Gen4 -- Jetting Station
Slava Chuhovich
November 2013
Copyright © 2013 Stratasys Ltd. All rights reserved.
Company Confidential

## Slide 2: Basic architecture
Copyright © 2013 Stratasys Ltd. All rights reserved.
Company Confidential
Tester application (PC)
OCB2
OHDB2
Head
Head drive card
x4
RS232
RS232
MSC
I²C
MSC
MSC
MSC

## Slide 3: Scope of work
Copyright © 2013 Stratasys Ltd. All rights reserved.
Company Confidential
Tester application (high level)
  User interface – complete redesign.
  Basic functionality, based on existing tester.
  New requirements (data arrangement, strobe, double pulse, etc.... ).
  Communication with OHDB2 board. New messages and registers.
  Voltage calibration algorithm
OHDB2 MCU firmware
  Low level procedures (fire all, etc…).
  New FPGA registers and head driver card logic.
  Temperature “ramp-up” control.
  Support 12 block filling thermistors, and their operation logic.
  Writing to a section of an EPROM for each head half.
  Switching between head halves for voltage calibration.
  Communication with PC. New messages and registers.
OCB2 MCU firmware
  Support for at least 4 MSC cards (8 pumps x2 for redundancy + 2 for dual waste).
  Support for 16 pumps and logic.
  Implement new “filling monitoring” for new block configuration (12 thermistors and their operation modes).

## Slide 4: Pre-requisites
Copyright © 2013 Stratasys Ltd. All rights reserved.
Company Confidential
For implementation
  Jetting station requirements from Meir
    Initial requirements available from 8/2013
    Detailed requirements not yet available
  Detailed spec and requirements from electronics department
    Not yet available
  Final block configuration thermistors / flooding wise
  Final pumps and MSC cards configuration
For integration
  OHDB2 board
  Head drive boards
  Printing block
  OHDB2 FPGA firmware

## Slide 5: Schedule
Copyright © 2013 Stratasys Ltd. All rights reserved.
Company Confidential
Resources
  1 dedicated developer
Schedule
  Work start
    Tester application – 9/2013
    Hardware MCUs – as soon as requirements are ready
  Work end – 1/2014
Risks
  Readiness of pre-requisites
    Software requirements – must be ready 10/2013 to meet schedule
    Hardware requirements – must be ready 10/2013 to meet schedule
  Readiness of hardware for integration
    Hardware – must be ready 11/2013 to meet schedule
  OCB2 related content
    Might be improved by ~2 weeks, by adding additional developer

## Slide 6
Thank You
Copyright © 2013 Stratasys Ltd. All rights reserved.
Company Confidential