## Slide 1: XL-C Project Review SW Content
July 21th, 2013
Copyright © 2013 Stratasys Ltd. All rights reserved.
Company Confidential

## Slide 2: XL-C Milestone 2 (Jetting Station)
Copyright © 2013 Stratasys Ltd. All rights reserved.
Software - Milestone 2 (SHS independent) |  |  | 
Task | Duration | SW Content | Pre-requisites
Tester adaptation | 2 MM | Additional Special FPGA code may be required. | Spec. OHDB2 and Data card final hardware schematics.
OHDB2 MCU Software | 1 MM | Not including ethernet. | Spec. OHDB2 and Data card final hardware schematics.
HW-SW integration | 1 MM |  | Final hardware.

## Slide 3: XL-C Milestone 2 (Jetting Station)
Copyright © 2013 Stratasys Ltd. All rights reserved.
Tester application adaptation and OHDB2 MCU software:
  High level tester application -- 2 month
    Spec available from Meir – CDR at 8/2013
      Basic functionality
      GUI
      New requirements compared to existing tester application
      Communication with OHDB2 board
  Low level implementation – 2 month (assuming similar design to E1/E3)
    No spec available: OHDB2 and head cards final hardware schematics
      PDR / CDR
      Low level procedures (Fire all …)
      New FPGA registers and head driver cards logic
      Hardware software integration (final hardware needed)

## Slide 4: XL-C Milestone 3 (Gen4 on Triplex)
Copyright © 2013 Stratasys Ltd. All rights reserved.
Software - Milestone 3 (SHS independent) |  |  |  | 
Task | Duration | SW Content | Pre-requisites | PDR / CDR
New Nozzles mapping | 1 MM |  | Print Head/Block spec | 1 week
New printing sequencers | 2 MM |  | PQ spec | 2 weeks
New Purge / Wiping Sequence | 1 MM |  | Spec | 1 week
Heads voltages calibration | 2 MM |  | Spec | 1 week
Configurable PH | 3 MM | Using same exe/code for E1 & G4 | Discuss if has benefit and how to do it. Depends also on Flooding/non Flooding. | 1 month
Simulator for OHDB2 | 1 MM |  | Final hardware schematics. | 1 week
Integration on the machine |  |  | Machine | NA

## Slide 5: XL-C Milestone 4 (No SHS Printing Mode)
Copyright © 2013 Stratasys Ltd. All rights reserved.
Software - Milestone 4 |  |  |  |  | 
Task | Block - Flooding | Block - Non Flooding | SW Content | Pre-requisites | PDR / CDR
Heads Filling Calibration Wizard | 1 MM | 2 MM |  | Spec | 1 week
Wiper Calibration Wizard | 1 MM | same |  | Spec | 1 week
Head Alignment Wizard | 1 MM | same |  | Spec | 2 weeks
Ethernet PC – OHDB data path communication | 6 MM | same |  | Spec | 1 month
Vacuum Calibration Wizard | 1 MM | 2 MM | Common to block / Per chamber | Spec | 1 week / 2 weeks
MRW | 3 MM | same |  | Spec | 2 weeks
Shutdown Wizard | 1 MM | same |  | Spec | 2 weeks
Printing Position Wizard | 1 MM | same |  | Spec | 1 week
BIT (Filling, Data …) | 1 MM | same |  | Spec | 1 week

## Slide 6: XL-C Milestone 4 – Ethernet data path
Copyright © 2013 Stratasys Ltd. All rights reserved.
Ethernet PC – OHDB data path communication -- 6 month:
  Code infrastructure to be able to use Ethernet or Data PCI by parameter selection
  UDP / IP connection implementation
  Data path implementation over UDP
  Transfer protocol implementation (error detection, retries …)
  UDP error and status handling
  BIT: new data path tests
  OHDB MCU: FPGA and PHY initialization
  Statuses handling returned from FPGA / PHY
  Additional required changes to OHDB MCU software
  Protocol to transfer VHDL firmware to FPGA over UDP (possibility)
  Integration with final hardware

## Slide 7: XL-C Milestone 4 (SHS Printing Mode)
Copyright © 2013 Stratasys Ltd. All rights reserved.
Software - Milestone 4 |  |  |  |  | 
Task | Block - Flooding | Block - Non Flooding | SW Content | Pre-requisites | PDR / CDR
SHS operation mode | 6 MM | same | Modes manager, Material per mode, System operation … | Spec | 3 weeks
SHS 600 DPI Y Sequencer | 1 MM | same |  | Spec | 2 weeks
MRW | 3 MM | High risk | From Connex/Triplex experience | Spec | 1 week / 3 months
HSW / HOW | 6 MM | High risk | Due to relation to MRW | Spec | 1 week / 2 months
UV calibration wizard | 4 MM | same |  | Spec | 2 weeks
SHS Advanced Licensing | 2 MM | same |  | Spec | 1 week
Objet Studio | 3 MM | same | New mode, Estimations, Flexible parameters. Not including 64-bit. | Spec | NA

## Slide 8: Why SHS support is problematic on NFLB
Copyright © 2013 Stratasys Ltd. All rights reserved.
Much less efficient material-wise
  Because of the extra piping to rinse.
  MRW Cannot optimize between Model 1 / Model 2.
Triplex M3 housings should be mechanically changed to become M/S dual-purpose.
Mandatory to perform SHS mode Printing with 4 valid inserted Tanks.
  2 Model + 2 Support
Mandatory to perform SHS mode Printing with balanced Tank weights.
  Model 1 cartridge weight = Model 2 cartridge weight
  Support 1 cartridge weight = Support 2 cartridge weight
Eden Block
Connex Block
Triplex Block (Flooding)
NFLB
S
M
S
M2
M1
S
M3/S
M2
M1
S
M3/S
M2
M1

## Slide 9: MRW & HOW on Non Flooding supporting SHS Explanation of the long EE
Copyright © 2013 Stratasys Ltd. All rights reserved.
Acronyms: FLB – Flooding Block NFLB – Non Flooding Block
Same code should support FLB & NFLB & SHS
      What if code is “split”? If Block related code is split between Triplex and XL, most Wizards will follow suit and we’ll end up with two separate development branches, one for Triplex FOM, and one for XL FOM.
  Why can’t we treat NFLB as a “private case” of FLB? NFLB cannot be constructed as a private case of FLB, because the logic required for supporting SHS mode is different. (Printing, MRW, HSW, SHD)
  So, FLB code can be “generalized” to support SHS logic when operating in a “non-flooding mode” This can be done. But the EE is large because of the complexity of this module.
  Note that EE for redeveloping code for NFLB only will be much smaller. But it will require that the same block will be used in all machine types. (Triplex & XL)

## Slide 10: Thank You
Copyright © 2013 Stratasys Ltd. All rights reserved.